## Sheet1
ES = max(EF of predecessors) |  | Activity ID |  | EF = ES+D |  |  |  | Two paths:
[8 empty] | abcfj |  | 42 Days
TS = LS - ES |  | Activity Description |  | FS = ES of Earliest Succcessor - EF |  |  |  | abcdefj |  | 59 Days |  | Critical Path
LS = LF - D |  | D = Activity Duration |  | LF = min(LS of successors)
| 0 | a | 5
| 2 | Datbase Creation | 0
| 2 | 5 | 7
6
| 5 | b | 7 |  | 7 | c | 22 |  | 24 | f | 39
| 2 | Data QA | 0 | 2 | 2 | Report Creation | 2 | 2 | 5 | Dashboards Published | 0
| 7 | 2 | 9 |  | 9 | 15 | 24 |  | 29 | 15 | 44
6
[5 empty] | 22 | d | 24 |  | 24 | e | 39 |  | 39 | j | 44
[5 empty] | 5 | Dashboard Creation | 0 | 2 | 5 | Gateways & Network Established | 0 | 2 | 5 | Dashboards Deployed | 5
[5 empty] | 27 | 2 | 29 |  | 29 | 15 | 44 |  | 44 | 5 | 49